Master of Science in Software Development

Capstone Project Handbook

Contents

Purpose of the Capstone Project	2

Technology Requirements	2

Project Timeline	2

Selecting a Project	3

Milestone 1: Project Proposal and High-Level Planning Phase	4

Milestone 2: Requirements Analysis Phase	7

Milestone 3: Technical Design Phase	8

Milestone 4: Development Phase (Coding and Testing)	13

Milestone 5: Final Development and Project Presentation Phase	15

Academic Integrity	16

Plagiarism	16

Sources of Information and Use of Reference Sources	16

Intellectual Property (IP)	17

References	17

# Purpose of the Capstone Project

The vision for the capstone experience is to develop a project that can be used to demonstrate individual knowledge, skills, and abilities within a specified field, as well as communicate to both technical and nontechnical audiences. The capstone project will be a tangible artifact students will refer to when interviewing for a job or enhancing their career options.

# Technology Requirements

Each student will independently determine the software and technologies needed for the project, with guidance as necessary by faculty. Use of free (open source) software is encouraged. The usual tools, such as MS Office, will be used for creating documentation and presentation materials.

Deliverables will be uploaded to a GCU-approved GIT repository, such as Bitbucket or GitHub, and possibly an app store, depending upon the nature of the project. For example, students would need access to the Apple Store or Google Play for smartphones if the project were a mobile app.

Bitbucket, GitHub, and GitLab are examples of GIT repositories sites, where all aspiring and experienced programmers post their accomplishments. All approved GIT repositories and policies are documented in the Student Success Center. As a reminder, and per GCU policy, all of your GIT repositories should be made private and the repository shared with your instructor. Capstone projects may be marketable products; therefore, students need to be exposed to areas that promote these products and where potential employers could look at their work. Students will consult their instructor to ensure that all student-created work is published in compliance with GCU regulations, while recognizing the student's ownership of the intellectual property rights.

# Project Timeline

The following are the deliverables for the Capstone Project as part of the Master of Science in Software Development program. Students are encouraged to initiate discussions with faculty regarding the ideas they have for their project. The deliverables for the Capstone Project are spread over 5 milestone assignments within the MSSD program and embedded within the various courses in the program. In SWE-520, you will get an overview of the Capstone Project expectations, along with this handbook that is customized for your program. It should also be noted that the appropriate templates for the various courses with deliverables will be available in the Student Success Center. The following table outlines the courses in which specific milestone assignment deliverables will be due.

It should be noted that in every course in the program where there is a milestone assignment, a DQ in each topic will be dedicated to the Capstone Project in order for students to report their project status via an Agile Scrum-like standup. This will always be DQ1 of the week and will be due on Day 3. The second DQ of each week will be due on Day 5. DQ2 will be associated with the course content.

It should also be noted that in every course in the program where there is a milestone assignment, 2 assignments will be required for submission. In Week 2 of each course, there will always the first Capstone Milestone assignment. Ideally, the students will be required to have at least 50% of the current milestone completed for this assignment due date. Then in Week 7 of each course, there will always be the second Capstone Milestone assignment. The student needs to complete each milestone assignment in the topic in which it is due because each assignment is assessed and accounts for the total. Auto-rubrics for each milestone will used to access the assignments. The following outlines the milestone deliverables:

| Course Title | Embedded Milestone Assignments |
| --- | --- |
| UNV-507 Introduction to Graduate Studies in CSET |  |
| SWE-520 Advanced Software Engineering Fundamentals | Introduction to Capstone Project |
| SDD-610 Software Design and Architecture |  |
| SWE-530 Advanced Software Architectures | Milestone 1: Draft Project Proposal Milestone 1: Final Project Proposal |
| SWE-540 Advanced Software Management & Concepts | Milestone 2: Draft Requirements Milestone 2: Final Requirements |
| SDD-620 Advanced Database Design and Administration |  |
| SDD-630 Mobile Software Development | Milestone 3: Draft Design Milestone 3: Final Design |
| SDD-640 Secure Coding | Milestone 4: Development Iteration 1 Milestone 4: Development Iteration 2 |
| SDD-680 Software Maintenance and Testing | Milestone 5: Final Project Development Milestone 5: Final Project Presentation |

# Selecting a Project

Defining the Project

You first need to clearly state the purpose of the project. Is the project intended to solve a particular problem? Is the project a game? Does the project explore a particular concept or technology? Is the project part of a larger solution for a workplace or business application?

If the project is intended to solve a particular problem, explain why the project is needed. What is the current process for solving the identified problem, and how will your project improve this process? Is the project final deliverable a complete product or the implementation of an (original) algorithm?

Project Examples

- Make a social networking site

- Create an online store site

- Make an iPhone, iPad, or Android mobile application

- Create an Online Voter Registration application

- Create a game

- Create a business application

- Create a scientific simulation

- Develop an augmented reality environment

- Build a visual computing environment

- Build a decision support system

- Implement a substantial algorithm published in a peer-reviewed journal

Project Guidelines

Successful project completion will be measured by the following criteria:

- Submission of all project components within the established deadlines

- Resource utilization within the initial design and plan, if applicable

- Meeting the desired performance/technology level as agreed upon by the student and instructor

- Utilization of the assigned resources effectively and efficiently

- Final presentation

Your project will begin with a Project Proposal and initial high-level planning. You will then develop the functional and non-functional requirements in a Requirements Specification. Next, you will develop a technical solution in Technical Design Specification. And finally, you will develop all the code and test the code over 2 releases, culminating in a final Project Presentation.

# Milestone 1: Project Proposal and High-Level Planning Phase

Objective: The goal of the project proposal plan is to identify the purpose of the project, outline the work to be done, and design a timeline for completing the work. The project proposal plan will contain a management plan, technical approach, and resources needed to complete the project tasks within the allocated time and budget. In addition, the project proposal plan should include a cover page that contains, at a minimum, the project title, author, course number, instructor name, document revision number, and date, along with a 3- to 5-sentence abstract that provides an overview of the project and introduces the reader to the document.

Your capstone project will need to be approved by your instructor for you to continue developing your project. A Capstone Project Proposal template can be found in the Student Success Center for SWE-530.

Deliverable: Submission of the Capstone Project Proposal using a template that is included in the Student Success Center. Refer to the information below for additional details on each section of the capstone proposal form.

General Information

The general information section of the Capstone Project Proposal will include the following:

- Cover Sheet: Project name, author, course number, instructor name, document revision number, and date the project proposal form is submitted.

- Project Abstract: 3- to 5-sentence abstract that provides an overview of the project and introduces the reader to the document.

- Initial features (i.e., Project Scope) that will included, both in scope and out of scope features.

- Initial Technologies that will be used for the project.

- Initial high-level Project Plan.

- Initial high-level Solution Design.

- Risk Mitigation Plan.

Project Overview and Project Objectives

The Project Overview and Project Objectives section of the Capstone Project Proposal states the business case or the problem that this project will be solving.

Example: The purpose of this project is to develop an online voter registration application that allows citizens to register to vote from any location where web access is available. The goal is to develop a secure application that is easy to access and use so that a wider population will have the ability to register to vote.

Background is one of the key characteristics of a project—explain why the project should be initiated, what the prerequisites are, and what results are supposed to be obtained at the successful completion.

Add a few sentences about the high-level business need or justification for the project, as well as how it originated and other background information. While this information may be obvious to you and the project sponsor, you should be aware that a scope of work is often distributed well beyond the immediate project audience. This background clarifies the usefulness of the project to someone who is not familiar with the project.

Example: Fabrikam, Inc. is migrating its current fabrication design system to new hardware and software platforms. Fabrikam, Inc. employees designed and developed the current Fabrikam-D system, which uses Fortran and runs on obsolete hardware. The Fabrikam-D system produces schematics and bills of material for fabrication jobs.

This project plan is a reference for all project personnel to guide the project through its successful completion to achieve Fabrikam, Inc.'s business and system objectives. After individually reviewing this version of the project plan, Fabrikam, Inc. stakeholders will meet to approve the approach before the project begins.

Project Scope

The Project Scope section of the Capstone Project Proposal states the scope of the project, defining the initial features that will be in scope and also out of scope for the project. Include details about the project, such as:

- Is it a real time system?

- Is it all screen-based?

- What reports can be produced?

- Where does the information come from?

- What manipulation is required for the data?

- Does it store data?

- How will the system manage security?

Project Completion

The Project Completion section of the Capstone Project Proposal describes what measures will be used to calculate project success, to include completion criteria, assumptions, and constraints.

Completion criteria are explicit goals that must be attained to call an element of a project, or the entire project, "complete."

Example: Successful Project Measurements for the Online Voting System

- Developed within the time allocated

- Developed within cost

- Meets the desired performance/technology level

- Utilized the assigned resource effectively and efficiently

- Customer approval and acceptance

- No disruption to the main workflow of the organization

- Coincides with the corporate culture

Important Notes: There can be projects in which performance is irrelevant because the main accomplishment is a product's completion (i.e., an algorithm). Therefore, the issue of measuring performance versus product completion must be decided and expectations set at this time. In other cases, students will work on projects just for themselves so there will be no approving party for the acceptance test final report. The instructor should help the student address and document this before moving to Milestone 2.

Project assumptions are events and circumstances that are expected to occur during the project life cycle for successful implementation and completion. Although assumptions are the driving force that determines project success, typically they are outside the total control of the project team. Project assumptions are accepted as true, often without any proof or demonstration.

Example: The online voting system is a new website; it is anyone's guess what the demand will be. What should the performance goal be in terms of concurrent users? The server must be able to handle the load for the number of concurrent users while maintaining performance.

Constraints are limitations affecting the project. Examples include timelines, resource availability, funding, and other important factors that affect project success.

Project assumptions and constraints tend to exist around project resource availability or competence. That is why, when developing a description of assumptions and constraints, try to give extra consideration to project cost, timing, and human-related issues.

Example: There is an unknown delivery timeframe for a key project component that would directly impact the scheduling critical path.

Important Note: There can be projects in which performance is irrelevant because the main accomplishment is a product's completion. Therefore, the issue of measuring performance versus product completion must be decided and expectations set at this time.

Acceptance by whom is also an issue that must be decided in the proposal phase. Many students will work on projects just for themselves, so there will be no acceptance. The mentor/advisor should address this question early on in the project.

Project Controls

The Project Controls section of the Capstone Project Proposal defines the potential risks and lists steps to prevent the risk from occurring, or the steps to minimize the chances of it happening.

This section describes how the end user will be involved in the software development. Include relevant information about meetings, reviews, and presentations.

Project Schedule

The Project Cost and Schedule section of the Capstone Project Proposal sets an initial high-level schedule by implementing work breakdown structure and task time estimates. It will be essential in this section to create a timeline (or Gantt chart) with dates for completion of key components of the project. The timeline should also include any Proof of Concept subprojects that need to be planned to reduce risks within the project.

Issue Log

The Issue Log section of the Capstone Project Proposal creates and maintains an issue log to identify and monitor project issues.

Project Solution Design

The Project Solution section of the Capstone Project Proposal defines the initial high-level technical solution for the project that ties together the high-level features of the project and the technologies that will be used in the project.

# Milestone 2: Requirements Analysis Phase

Objective: In the Requirements Analysis Phase, the requirements gathered in the planning phase are used to address components such as report definitions and layouts, screen definitions and layouts, data element definitions, workflow diagrams, and security matrices. The requirements document (a.k.a. Requirements Specification), like the Project Proposal plan and for consistency, should include a cover page that contains, at a minimum, the project title, author, course number, instructor name, document revision number, and date, along with a 3- to 5-sentence abstract that provides an overview of the project and introduces the reader to the document.

Your Requirements Specification will be developed in SWE-540.

Deliverable: Submission of the Project Requirements Specification.

Refer to the information below for additional details on each section of the Project Requirements Specification. A Project Requirements Specification template can be found in the Student Success Center for SWE-540.

Special Note: Depending on the project, portions of this milestone may not be applicable. In cases like these, work with the instructor to determine the components of the project that may replace this step. The instructor will determine what documentation is needed and how this documentation will be assessed.

User Stories - Functional Requirements

A user story describes a sequence of actions a project performs thatroject s an a system technoligies ative text of tuse cases tells the store of how a user and the system interaacte in aa simple,shows provide an observable result of a value to a particular actor. The user stories will be formatted using standard Agile Scrum format: As a [USER/ROLE], I want [FEATURE] so that [RATIONALE FOR FEATURE]. The user stories should completely and clearly address all of the features, functionalities, and capabilities of the system or application that is being defined.

User Stories - Non-Functional Requirements

User stories should also be defined for non-functional requirements (NFRs). A list common NFRs can be found at https://en.wikipedia.org/wiki/Non-functional_requirement. Review and provide the appropriate NFRs applicable to the project, defined as use cases or as a narrative using user stories. If necessary, the use cases can be documented in an external Excel spreadsheet with a reference to the document provided in the Requirements Specification.

# Milestone 3: Technical Design Phase

Objective: In the Technical Design Phase, the formal technical approach and detailed design is completed. The design could also include report definitions and layouts, screen definitions and layouts, data element definitions, workflow diagrams, and security matrices. The Technical Design Specification, like the Project Proposal plan and for consistency, should include a cover page that contains, at a minimum, the project title, author, course number, instructor name, document revision number, and date, along with a 3- to 5-sentence abstract that provides an overview of the project and introduces the reader to the document.

Your Technical Design Specification will be developed in SDD-630.

Deliverable: Submission of the Technical Design Specification.

Refer to the information below for additional details on each section of the project's Technical Design Specification. A Technical Design Specification template can be found in the Student Success Center for SDD-630.

Special Note: Depending on the project, portions of this milestone may not be applicable. In cases like these, work with the instructor to determine the components of the project that may replace this step. The instructor will determine what documentation is needed and how this documentation will be assessed.

Title Page

The Technical Design Specification, like the Requirements Document and for consistency, should include a cover page that contains, at a minimum, the project title, author, course number, instructor name, document revision number, and date, along with a 3- to 5-sentence abstract that provides an overview of the project and introduces the reader to the document.

Final Technical Requirements

Provide a listing of the final technical requirements that the system must fulfill. List these requirements and include a brief description. Follow the listing of technical requirements with a listing and explanation of the software and/or hardware that is necessary to meet the requirements.

Overview of Design Concepts

Provide the high-level design of the proposed solution with supporting narrative text. This document should include mock-up screenshots for the proposed user interface screens, pseudocode, and/or flowcharts that show the logic for the program, as well as the anticipated process flow. The purpose of this document is to allow the stakeholder to approve the concepts before committing resources to the technical design and implementation. If there is no stakeholder, then provide a personal statement and explanation indicating the design concepts are satisfactory.

Detailed Solution Architecture

Provide a detailed overview of the system architecture, including:

- An overview of how the proposed design fits into the overall project structure.

- Object and data element definitions, including a description of all objects with UML diagrams. Describe the purpose and characteristics of all data elements.

- Additional diagrams as needed for your particular system, such as entity-relationship diagrams, workflow diagrams, database schema, and so on.

- Collaboration diagrams and/or sequence diagrams to show the workflows of components/packages/classes inside the component.

- Algorithm descriptions where possible.

- Detailed final specifications for all screens, interfaces and integration points, processes, conversions, reports, and any required modifications to existing systems.

- Any solution configuration changes that will be required to develop and implement the proposed project, including hardware and software technologies.

- Description of the approach and resources required to assure system security, if relevant.

Keep in mind, the purpose of the detailed solution architecture is to provide sufficient information for a developer to produce the system.

System Logical and Physical Models

Provide a diagram of the logical architecture and the physical architecture of the system. This diagram should reflect the business rules of the application, if applicable, and illustrate the flow of information through the system. The logical design should be abstract; that is, it should not include any implementation details. The purpose of the logical model is to map data from its source to its appropriate destination, following the system decision structure. The logical model describes how the system works in terms of function and logical information. The physical design should map the logical design onto a physical design that includes servers, databases, network protocols/ports, and connectivity to any third-party systems.

Reports

Provide a listing of the reports the system will provide. This section can be removed if not applicable for your project. For each report, include details such as:

- Title and purpose of each report

- Data included in each report

- Formatting requirements

- Frequency

Example:

| <Report Title> |  |  |
| --- | --- | --- |
| Display Value | Variable or Field | Format Notes |
| Customer ID | Customer.ID | "xx-xxxxxxx" |
| Customer Plan | Customer.planID | Premier, Standard or Basic |
| Customer Data Usage | Customer.dataMB | Number, 2 decimal places |
| Customer Bill | Customer.amtDue | Number, 2 decimal places |

Depending on the project, if a list of reports in not applicable, consider providing documentation similar to the following examples:

- An analysis of an algorithm and proof of its computational complexity

- A visualization of a process

Screen Definitions and Layouts

Provide a draft of each user interface screen required by the system. This section can be removed if not applicable for your project. These interface "sketches" will be refined in the design phase. Diagrams should include components such as, but not limited to:

- Title

- Toolbars

- Date entry fields

- Content, such as text, charts, tables, etc.

Example:

Depending on the project, if screen definitions and layouts are not applicable, work with the instructor to define the components of the project that may replace this step. The project may be theoretical, practical, software development, or a mobile application. Flowcharts, mathematical proofs, and technical diagrams are suitable substitutes for projects that do not involve creating complete GUI-based applications.

Security

Discuss the security issues relevant to the system. If there are no security issues, explain why. Provide a matrix that illustrates the permissions/access rights of different types of users on the system.

Helpful Hint: If there are no immediately evident security issues, it does not mean there aren't any. An often-overlooked security issue is badly designed software that can be exploited by hackers to penetrate a system even if the hacking objective is a different component of that system.

Ensure that you are properly addressing the security issues or the absence of security issues. Overall, explain the nature of any security issues that may impact the project, or why there will be no such impact.

Example:

# Milestone 4: Development Phase (Coding and Testing)

Coding Objective: The main objective of the development phase is to build the project code and create the documentation based on the requirements and analysis decisions. This phase transforms the design documents into an executable program. System entities such as objects, data tables, classes, and the like are developed. These entities are then gathered and connected together (integrated) to create a working application. The application is placed on a staging server for testing. Code reviews are generally part of the development phase.

Coding Deliverables: Submission of the following elements:

- Implementation Plan

- Functional Requirements Mapping (i.e., Traceability Matrix)

- Test Plan and Test Cases

- Zip file of the Source Code modules

- A URL to an Application Demonstration via a screencast video

Refer to the information below for additional details on each deliverable for this phase.

Two iterations of code releases (i.e., coding and testing) will be made in both SDD-640 and SDD-680, where the final release in SDD-680 will actually be your final project. All templates for this milestone will be provided in the Student Success Center for SDD-640.

Coding Special Note: Depending on the project, portions of this milestone may not be applicable. In cases like these, work with the instructor to determine the components of the project that may replace this step. The instructor will determine what documentation is needed and how this documentation will be assessed. If major portions of the project consist of theoretical components (e.g., algorithm design), coding may be substituted, in consultation with the project advisor, with mathematical proof(s) and analysis of correctness, or other mathematical treatment of the subject.

Implementation Plan

The implementation plan provides a detailed outline of activities necessary to ensure the delivery of the planned user stories for this milestone assignment. This course does not specify which planning delivery methodology or tools you are required to use in your implementation plan. It is recommended you seek advice from your instructor. The following are some suggestions you can follow for your implementation plan:

- Use a formal methodology, such Agile Scrum or Kanban.

- Planning tools could include, but are not limited to, Microsoft Excel or your own Word template, Atlassian Jira and Confluence (you can get a free account), or other online tools such as monday.com or notion.so.

- At a minimum, your implementation plan should include the follow elements:

| Use Case or User Story | List of detailed Development Tasks | Estimate (hrs.) | Actual (hrs.) | Percent Complete |
| --- | --- | --- | --- | --- |

Percent of User Stories completed for this release and your project:

Percent of User Stories taken out of scope for this release and your project:

Mapping of Functional Requirements

This exercise ensures that all functional requirements have been satisfied by creating a mapping for each requirement to the Technical Design Specification, appropriate code module(s) that satisfies the requirement, and the test cases used to test the requirement. This is referred to as Traceability; a template for this can be found in the Student Success Center for SDD-640.

Example

| (Use Case/User Story) Monthly bill sent by email | (Technical Design) Page or section where designed | (Code Module) Class and Method where implemented | (Test Case) Test Case number from the Test Plan |
| --- | --- | --- | --- |

Source Code Listing

Provide a listing of the source code for the project. Include a brief description of all classes and files. Code should follow industry best practices, formatting, and comment style appropriate for the programming language.

Test Plan and Test Cases

Develop test cases for all modules. Test modules as part of development process and continually revise the code as necessary. A Test Plan and Test Case template can be found in the Student Success Center for SDD-640.

Example of Test Case Listing

| Test Case Name: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Priority: |  |  |  |  |  |  |
| Module: |  |  |  |  |  |  |
| Test Objective: |  |  |  |  |  |  |
| Step |  | Test Name | Test Steps | Test Data | Expected Results | Test Pass/Fail |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |

Testing Objective: The functional testing phase ensures the application functions as requested. In all testing stages, defects are identified and returned to the development/coding phase for correction.

Testing Special Note: Depending on the project, portions of this milestone may not be applicable. In cases like these, work with the instructor to determine the components of the project that may replace this step. The instructor will determine what documentation is needed and how this documentation will be assessed. If major portions of the project are not code, the testing may consist, for example, of proof by induction that an algorithm works the way it is envisioned—consult your project advisor.

# Milestone 5: Final Development and Project Presentation Phase

Coding Objective: The main objective of this development phase is to deliver the final project code and create the final documentation based on the requirements and analysis decisions. Much like Milestone 4, this phase transforms the design documents into an executable program. System entities such as objects, data tables, classes, and the like are developed. These entities are then gathered and connected together (integrated) to create a working application. The application is placed on a staging server for testing. Code reviews are generally part of the development phase.

All templates for this milestone will be provided in the Student Success Center for SDD-680.

You will also provide a short screencast video (10–15 minutes), per GCU policies used in previous classes, that demonstrates all functionality that is working in the project up to this point.

Final Coding Deliverables: Submission of the following elements:

- Implementation Plan

- Functional Requirements Mapping (i.e., Traceability Matrix)

- Test Plan and Test Cases

- Zip file of the Source Code modules

Final Project Deliverables: Submission of the following elements:

- Updated project artifacts, including updates as needed to the Project Proposal, Requirements Specification, and Technical Design Specification, to ensure all final project artifacts align with the final implementation.

- Formal PowerPoint Presentation that includes a short screencast video demonstration.

- URL to the screencast video demonstrating the entire finished project.

# Academic Integrity

For detailed information, refer to the GCU Academic Integrity webpage.

# Plagiarism

Students are encouraged to use code created by others, if explicit written permission is given. It is common practice for programmers to use each other's code. Refer to Creative Commons license. GitHub is a place where everyone uploads and everyone borrows others' work. It is acceptable as long as these are only small portions of the code or essential libraries that allow the student to build upon. The student should consult with the advisor/mentor and obtain written approval from the mentor for the use of borrowed code.

For detailed information regarding the University's Plagiarism Policies, refer to the GCU University Policy Handbook.

Additional Resources

Grand Canyon University (n.d.). Plagiarism Video. http://tutorials.gcumedia.com/plagiarismVideo/vp02.swf

Grand Canyon University (n.d.). Plagiarism Prevention Tutorial. http://www.gcumedia.com/mediaElements/gcu-plagiarism-prevention-tutorial/v1.1/

# Sources of Information and Use of Reference Sources

The GCU Library is dedicated to supporting the University's educational mission with library services that support both course content and research assignments. The Library is proud to offer the following services:

- Ask A Librarian: Students, staff, and faculty can ask the Library for research assistance via phone, email, or chat. Librarians can help with personalized assistance with creating effective search strategies for research topics, basic database navigation, using the resource tools, including RefWorks and EndNote Web, personalized database accounts, RSS feeds, search alerts, APA formatting, persistent links, and more!

- Faculty Request for Group Library Instruction: Faculty can request general library instruction for their students or request customized information literacy instruction focusing on specific subjects and research assignments. The Librarians will instruct classes on navigation, search strategies, and using the library resources. Request in-person or online library instruction.

- Library Databases & Resources: Students, staff, and faculty can search on the Library's website for journal articles, ebooks and physical books, dissertations, streaming video and streaming music, using our extensive collection of databases and resources. They can also organize and manage their citations with bibliographic management software tools RefWorks or EndNote Web.

- Help & Tutorials: Library, database, and technical support tutorials are accessible on the Library's website: http://library.gcu.edu. The Library also offers webinars on Doctoral Research, Nursing & Health Sciences, Education Resources, Faculty, and Introductory webinars, which provide a guided tour of how to access and use the Library's resources.

- Interlibrary Loan (ILL): Any material not owned in the GCU Library can be ordered via ILL. The Library has many reciprocal sharing agreements with libraries throughout the country. There is no charge to GCU students for ILLs.

# Intellectual Property (IP)

For detailed information regarding the University's Intellectual Property Rights, refer to the GCU University Policy Handbook.

# References

Grand Canyon University. (2016). University Policy Handbook 2016-2017 http://www.gcu.edu/academics/academic-policies.php

Grand Canyon University. (2015). Academic Integrity. http://students.gcu.edu/academics/academic-integrity.php

Grand Canyon University. (n.d.). GCU Statement on the Integration of Faith and Work. http://www.gcu.edu/Documents/IFLW.pdf