Economic Analysis of Software Products and Processes, Software Cost and Scheduling

Ryan Coon

Swe-540

Professor Ali Wahid

June 17, 2026

Part 1: Projected time frame

Client Interview Questions

- What products will be sold on the website?

- Who is the target audience?

- What are the primary business goals for the website?

- Will the website operate locally, nationally, or internationally?

- What payment methods should be supported?

- Should customers create accounts before purchasing?

- Will guest checkout be available?

- What search and filtering capabilities are required?

- Should customers be able to leave reviews and ratings?

- What devices should the website support (desktop, tablet, mobile)?

- How should products be categorized?

- Should customers be able to save items to a wish list?

- What shipping options will be offered?

- How should order tracking work?

- Should promotional discounts and coupon codes be supported?

- How will administrators manage products?

- What reporting features are needed?

- Who will manage inventory?

- How should customer support requests be handled?

- Are there security or compliance requirements?

User Stories

US-01 - As a customer, I want to create an account so that I can save my personal information and order history.

US-02 - As a customer, I want to securely log in so that I can access my account.

US-03 - As a customer, I want to browse products by category so that I can find products easily.

US-04 - As a customer, I want to search for products so that I can quickly locate specific items.

US-05 - As a customer, I want to add products to a shopping cart so that I can purchase multiple items.

US-06 - As a customer, I want to complete a secure checkout process so that I can purchase products.

US-07 - As a customer, I want to pay using a credit card or digital wallet so that I can complete my purchase.

US-08 - As a customer, I want to track my order status so that I know when it will arrive.

US-09 - As an administrator, I want to add, update, and remove products so that inventory remains accurate.

US-10 - As an administrator, I want to generate sales reports so that I can monitor business performance.

Product Backlog

| Priority | User Story | Description |
| --- | --- | --- |
| 1 | US-06 | Checkout Process |
| 2 | US-07 | Payment Processing |
| 3 | US-05 | Shopping Cart |
| 4 | US-01 | User Registration |
| 5 | US-02 | User Login |
| 6 | US-03 | Browse Products |
| 7 | US-04 | Product Search |
| 8 | US-08 | Order Tracking |
| 9 | US-09 | Product Management |
| 10 | US-10 | Sales Reporting |

Release Backlog

| User Story | Description |
| --- | --- |
| US-01 | User Registration |
| US-02 | User Login |
| US-03 | Browse Products |
| US-04 | Product Search |
| US-05 | Shopping Cart |
| US-06 | Checkout Process |
| US-07 | Payment Processing |

Project Timeframe for Release Backlog

| User Story | Estimated Time |
| --- | --- |
| US-01 Registration | 3 Days |
| US-02 Login | 2 Days |
| US-03 Browse Products | 3 Days |
| US-04 Product Search | 3 Days |
| US-05 Shopping Cart | 1 Week |
| US-06 Checkout Process | 1 Week |
| US-07 Payment Processing | 1 Week |

Release Backlog Timeline

Sprint 1 – Weeks 1 – 2

US-01 Registration

US-02 Login

US-03 Browse Products

US-04 – Product Search

Sprint 2 – Weeks 3-4

US-05 – Shopping Cart

US-06 – Checkout Process

Sprint 3 – Weeks 5-6

US-07 – Payment Processing

Part 2: Project Opportunity Cost

Payback Period - The project will recover its initial investment of $7,200 in approximately 2.4 years, which is a reasonable timeframe for technology projects.

Discounted Cash Flow (DCF) & Net Present Value (NPV) - The total discounted cash flow over three years at a 10% discount rate is about $7,460.56. Subtracting the initial investment, the NPV is positive at $260.56, indicating the project is financially viable.

Cost-Benefit Analysis - The net benefit over three years is $1,800, with a benefit-cost ratio of 1.25, meaning the project returns $1.25 for every dollar invested.

Internal Rate of Return (IRR) - The IRR is approximately 12.04%, which exceeds the 10% discount rate, suggesting the project is expected to generate returns above the minimum required rate.

| Metric | Value |
| --- | --- |
| Initial Investment | $7,200 |
| Payback Period | 2.4 Years |
| Net Present Value (NPV) | $260.56 |
| Benefit-Cost Ratio | 1.25 |
| Internal Rate of Return (IRR) | 12.04% |

Part 3: Go/No-Go Decision Analysis

The proposed development of an e-commerce platform using Agile Scrum methodology presents a compelling opportunity for investment, but it is essential to analyze the opportunity cost and evaluate whether the project should proceed based on financial metrics. This analysis considers the initial development cost, projected cash inflows, and key financial indicators such as payback period, discounted cash flow (DCF), net present value (NPV), cost-benefit analysis, and internal rate of return (IRR).

The initial investment required for the project is estimated at $7,200, covering the development of core functionalities including product browsing, user account management, and secure checkout processes. These features are critical for establishing a functional and user-friendly e-commerce platform that can attract and retain customers. The project timeline is projected to span 10 working days, reflecting an efficient development cycle facilitated by Agile Scrum practices, which emphasizes iterative delivery and continuous feedback.

From a revenue perspective, the project is expected to generate annual cash inflows of approximately $3,000 over a three-year period. This projection assumes steady growth in sales and customer engagement as the platform gains traction in the market. While these figures are estimates, they provide a basis for evaluating the financial viability of the project.

The payback period, which measures the time required to recover the initial investment from net cash inflows, is calculated at 2.4 years. This indicates that the project will recoup its costs within a reasonable timeframe, allowing the business to start realizing profits relatively early in the platform’s lifecycle. A payback period under three years is generally considered acceptable for technology projects, especially those with growth potential (Ross, Westerfield, & Jaffe, 2019).

More comprehensive financial evaluation is provided by the discounted cash flow analysis. By discounting future cash inflows at a rate of 10%, which reflects the opportunity cost of capital and risk associated with the project, the present value of expected cash inflows over three years is approximately $7,461. Subtracting the initial investment yields a positive net present value (NPV) of $261. A positive NPV suggests that the project is expected to generate value beyond its cost, making it financially attractive (Brealey, Myers, & Allen, 2022). The NPV accounts for the time value of money, ensuring that future earnings are appropriately weighted against current expenditures.

The cost-benefit analysis further supports the project’s viability. With total benefits estimated at $9,000 over three years against costs of $7,200, the net benefit stands at $1,800. This surplus indicates that the project’s returns exceed its costs, providing a financial cushion that can absorb unforeseen expenses or lower-than-expected revenues.

The internal rate of return (IRR), which identifies the discount rate that sets the NPV to zero, is estimated at approximately 12.5%. Since this rate exceeds the assumed discount rate of 10%, the project promises returns above the minimum required threshold, reinforcing the argument for proceeding with development (Damodaran, 2012). An IRR higher than the cost of capital typically signals a worthwhile investment.

However, opportunity cost must also be considered. By allocating resources to this project, the organization forgoes alternative investments or projects that might offer different returns or strategic benefits. The 10% discount rate used in the analysis implicitly reflects this opportunity cost, representing the expected return from the next best alternative. Given the positive NPV and favorable IRR, the opportunity cost of investing in this e-commerce platform appears justified.

Despite the positive financial indicators, decision-makers should also weigh qualitative factors such as market conditions, competitive landscape, and technological risks. Agile Scrum’s iterative approach mitigates some risks by enabling early feedback and adjustments, but uncertainties remain, especially in customer adoption and evolving regulatory requirements.

In conclusion, based on the financial analysis, the e-commerce platform project represents a Go decision. The payback period is reasonable, the NPV is positive, and the IRR exceeds the discount rate, all suggesting that the project is likely to generate value for the organization. The opportunity cost is accounted for in the discount rate, and the projected benefits outweigh the costs. While continuous monitoring and agile adjustments will be essential to address risks, the financial evidence supports moving forward with the development of the e-commerce platform.

References

Brealey, R. A., Myers, S. C., & Allen, F. (2022). Principles of Corporate Finance (14th ed.). McGraw-Hill Education.

Damodaran, A. (2012). Investment valuation: Tools and techniques for determining the value of any asset (3rd ed.). Wiley. https://suhaconsulting.com/wp-content/uploads/2018/09/investment-valuation-3rd-edition.pdf

Ross, S. A., Westerfield, R., & Jordan, B. D. (2019). Fundamentals of Corporate Finance (12th ed.). McGraw-Hill Education.